Select any team name you prefer.
Please enter your name as it appears in Blackboard.
This is the priority ranking for this feature, relative to all other features.

Lower integers are higher in prioirty.

The customer may add or (for unimplemented features) remove features and change priority rankings at the start of each sprint.
This is the sprint during which the grader will grade your implementation of this feature.

By the END of this sprint, you must have implemented this feature.

If this field is blank, then this is a bonus feature. If implemented, it will be graded after t
This is the professor's estimate as to the relative difficulty of this feature in "points".

Points are unitless, and only have meaning relative to other estimates (a 2 point feature is expected to take about twice as long as a 1 point feature).

In a re
Select the sprint number (1, 2, etc.) in which you plan to implement this feature. This is just for planning purposes, it won't affect your grade.

In Scrum, you only plan the current sprint, not future sprints, so you don't need to fill this in for any
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Leave blank initially (hint: Use the Delete key)
Select "In Work" when you begin designing and coding this feature.
Select "In Test" when this feature is fully coded and you are testing it.
Select Finished ONLY when the feature works well and is READY TO
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
Please enter 2 or 3 capital letters that will represent you in the "Assigned To" column on each Sprint Backlog tab of this spreadsheet.
Please enter your UTA student ID number.
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
This is just an arbitrary unique (per sprint) integer assigned to a task, used by the team to refer to that task.
The list contains the Feature IDs from the same column on the Product Backlog tab.

For each (ahem) Feature ID, create one or more rows in this table representing the tasks you need to complete to implement that feature.

For example, for a "Provide Help
Exactly ONE team member may be responsible for any task, and they will receive grade credit for their work.

If you have more than one person on your team, each member MUST select their initials for each task the agree to perform. Use this to ensure that
Select a Feature ID to the left. Then, in this column, list each discrete task needed to implement that feature.

Example tasks might be "create the Foo class", "add the Bar method to the (existing) Qux class", "Find icons for the task bar", "Update the m
Leave blank until task is begun.
Select "In Work" when started (for long tasks only).
Select Completed ONLY when this task is done.
    Select "Completed Day 1" if finished on the first day, and
    similarly for "Completed on Day 2" et. al.
This cell may only contain a valid status value (hint: use the drop-down selection list) or be left blank (hint: use the Delete key)
You may add any notes here that help understand the requirements and scope for this task
## Product Backlog
Product Name:	MICE Manager					Complete Fields in Green!!!
Team ID:	Water Bottle					Product Backlog Burn Chart / Sprints / Features Remaining at end of Sprint

	Team Member Name					Initials	Student ID
Required	Andy Tieu					AT	1001635126

Sprint #	Remaining	Completed This Sprint				Comment
0	39				Total	Total number of features (in column H)
1	39	0			1	Total features left at the end of Sprint #1
2	39	0			2	Total features left at the end of Sprint #2
3	39	0			3	...and so on
4	39	0
5	39	0
6	39	0

				Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
				Additional features may be proposed by the student but must be approved by the Product Owner in writing
				Sprints
Feature ID	Priority	Required	Bonus Points	Est	Planned	Status	As a...	I want to...	So that I can…	Notes
CF	1	1		5	1	In Test	Manager	Create a new ice cream flavor	Stock and sell dairy products	Base this off of an Item superclass (see design)
MXF	2	1		1	1	In Test	Manager	Create a new “mix in” flavor	Let Customers to add flavors to their ice cream	Base this off of an Item superclass (see design)
MX	3	1		2	1	In Test	Manager	Create a “mix in” request including amount to mix in	Let Customers vary how much mix ins are, uh, mixed in to the ice cream scoop	Include light, normal, extra, and drenched amounts of a mix in (via an enum); cost and price are presumed constant
SCP	4	1		13	1	In Test	Manager	Specify a scoop of ice cream	Mix a flavor of ice cream with mix ins	Include as many mix ins (with amounts of each) as desired; need regression or interactive tests at this point (hence high estimate)
GUI	5	2		13			Manager	Use a GUI instead of a terminal	Reduce training costs	This is the main window, with menu bar, tool bar, text data area, and optionally status bar; list orders in data area
IGUI	6	2		13			Manager	Use dialogs to create items	Reduce training costs	One dialog should server for all items with minor variations
CC	7	2		5			Manager	Create a new container	Stock and sell dairy products	Containers have varying maximum number of scoops permitted; cost and price are assumed to be zero
CS	8	2		8			Server	Create a serving of 1 or more ice cream scoops with mix ins in a container with toppings	Create dairy products to sell	Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and add to array list
LOGO	9	3		5			Customer	Slowly draw stylized logo with vectors as splash screen	Have a more attractive program launch	May use provided vector file or create your own (this gives practice with drawing on a canvas before the exam)
SAVD	10	3		8			Manager	Save all data to a default file	Ensure our data isn’t lost
LALL	11	3		8			Owner	Load data from a specified file	Franchise my company
SALL	12	3		5			Owner	Save all data to a specified file	Franchise my company
CTM	13	4		3			Manager	Create a new server	Staff the emporium
CB	14	4		2			Server	Create a new beloved customer	Keep track of our customers
CO	15	4		8			Server	Create an order of many servings of ice cream	Serve everyone in a customer party
CSB	16	4		1			Customer	Create a serving of ice cream in a container with toppings	Self-order and not have to deal with people	This just enables the Customer role to do what the Server can do in defining a serving…
COB	17	4		1			Customer	Create an order of many servings of ice cream	Self-order and not have to deal with people	...and order
CE	18	4		5			Manager	Create an emporium that stocks items and maintains a cash register	Manage the emporium	This includes item stocks, server and customer lists, and the cash register
MST	19	5		8			Manager	Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled)	Ensure each order is filled and payment collected
POS	20	5		5			Server	Show the servings in an order for the servers (what to prepare)	Know what to put into each serving in an order	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC	21	5		5			Customer	Show the servings in an order for the customer (what was ordered / how much it costs)	Verify that my order was taken correctly and see the price	This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
PIX	22	5		13			Customer	Add and display pictures for each item (container, ice cream flavor, and topping)	Better understand the menu	Store path and filename of image for each ice cream and mix in flavor, and display when ordering
CENEW	23			13			Owner	Create a new franchise	Franchise my company
CM	24			3			Owner	Create a new manager	Delegate management tasks to a pro
P&L	25			8			Manager	Add a Profit & Loss statement, showing all income, expenses, and total profit	Ensure that we’re making a profit and thus avoid bankruptcy
RI	26			5			Manager	Display an Inventory Report, listing every item and the quantity in stock	Ensure we don’t run out of any product and thus disappoint our customers
RTM	27			8			Manager	Display a Server Report, listing all info about each server including # of orders served	Better manage our team and reward productive team members
ETMS	28			8			Manager	Change a server salary	Offer promotions and pay bumps to motivate our team members
AI	29			8			Server	Restock items (ice cream flavor, container, and topping)	Ensure we can fill every order
PS	30			5			Customer	Show the components of a serving (container, scoops, and toppings) for verification	Ensure my order was taken correctly	Select serving in dialog (or data area if clever), then use toString method in a dialog to display details
RO	31			8			Manager	Create an Order Report, showing all pending orders (unfilled and filled but unpaid)	Better manage our production process
RB	32			5			Manager	Display a Customer Report, listing all info about each customer	Better attract repeat customers and handle complaints
EF	33			8			Manager	Edit an ice cream flavor	Improve our data and keep it synced to reality
EC	34			8			Manager	Edit a container	Improve our data and keep it synced to reality
ET	35			8			Manager	Edit a new topping	Improve our data and keep it synced to reality
ROA	36			3			Manager	Add Order Report option to show completed as well as pending orders	Review our order history seeking patterns to understand how to improve efficiency and profit
XI	37			21			Manager	Retire an item (no longer enable its selection for a new order, but keep in reports)	Remove items no longer offered from the menu
XT	38			13			Manager	Suspend a server (no longer allow their selection for an order or restock, but keep in reports)	Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT	39			5			Manager	Restore a server	Add a former team member tack into service

## Sprint 01 Backlog
Sprint #	1		Complete Fields in Green!!!
Start on	Sep 27		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 04		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1	CF		--> Add tasks to complete each feature for this sprint	In Work
2	MXF			In Work
3	MX			In Work
4	SCP			In Work
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint #	2		Complete Fields in Green!!!
Start on	Oct 04		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 11		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint #	3		Complete Fields in Green!!!
Start on	Oct 11		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Oct 18		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint #	4		Complete Fields in Green!!!
Start on	Nov 08		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 15		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint #	5		Complete Fields in Green!!!
Start on	Nov 15		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Nov 22		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0

Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint #	6	BONUS	Complete Fields in Green!!!
Start on	Nov 29		*** Create a new Sprint Backlog for EVERY SPRINT ***
End on	Dec 06		Sprint Burn Chart / Days / Tasks
Demo on	TBD

	Remaining	Completed (this day)
Total Tasks	1
Day 1 Left	1	0
Day 2 Left	1	0
Day 3 Left	1	0
Day 4 Left	1	0
Day 5 Left	1	0
Day 6 Left	1	0
Day 7 Left	1	0
			IMPORTANT: This is an optional sprint for students seeking additional points
Task ID	Feature ID	Assigned To	Description	Status	Notes
1			--> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84